## Sheet1
Week | Continous Integration | Continous Delivery | Esimation of dificulty/time
2022-04-01 | Create Azure account (if doesn’t exist) |  | Moderate considering the required access provided
2022-04-08 | Create the Cloud-Based Development Environment |  | Moderate
2022-04-15 | Create Project Scaffolding |  | Easy
2022-04-22 | Perform Local Test |  | Moderate
2022-04-29 | Enable Github Actions and replace yml code |  | Easy
2022-05-05 | Verify Remote Tests pass and take necessary screenshots |  | Easy
2022-05-06 |  | Get Flask Starter Code | Easy
2022-05-19 |  | Make predictions and logs | Moderate
2022-05-26 | Documentation | Documentation | Moderate
2022-06-03 | Demo | Demo | Moderate
2022-06-04 | Check the work | Check the work | Moderate
| Goals | Goals
| Set up Azure Cloud Shell | Continuous Delivery on Azure
| Configure GitHub Actions | Documentation
| Documentation | Demo
Demo