## Sheet1
Week | Continous Integration | Continous Delivery | Esimation of dificulty/time
2022-04-01 | Create Azure account (if doesn’t exist) |  | Moderate considering the required access provided (20 hrs)
2022-04-08 | Create the Cloud-Based Development Environment |  | Moderate (20hrs)
2022-04-15 | Create Project Scaffolding |  | low (10hrs)
2022-04-22 | Perform Local Test |  | Moderate (20hrs)
2022-04-29 | Enable Github Actions and replace yml code |  | Low (10-15hrs)
2022-05-05 | Verify Remote Tests pass and take necessary screenshots |  | Low (10-15hrs)
2022-05-06 |  | Get Flask Starter Code | Low (10hrs)
2022-05-19 |  | Make predictions and logs | High( 40hrs)
2022-05-26 | Documentation | Documentation | High (40hrs)
2022-06-03 | Demo | Demo | Moderate (40hrs)
2022-06-04 | Check the work | Check the work | Moderate (20hrs)
Quaterly plan | Goals | Goals | Esimation of dificulty/time
Q1 | Set up Azure Cloud Shell | Continuous Delivery on Azure | Moderate considering the required access provided (20 hrs)
| Configure GitHub Actions |  | Moderate (20hrs)
Q2 | Documentation | Documentation | Low (10hrs)
Q3 | Demo | Demo | Moderate (20hrs)
Q4 | Any improvements | Any improvements | Moderate (40hrs)
| Additional testing and QA | Additional testing and QA | Moderate (40hrs)
Yearly plan | Goals | Goals | Esimation of dificulty/time
In long run further improvements cn be done (next 3 years) | Building Docker Images, building Kubernetes namespaces and clusters | Building Docker Images, building Kubernetes namespaces and clusters | High - 1.5 year
| Deploying the code on Kubernetes Cluster | Deploying the code on Kubernetes Cluster | High - 1.5 year